Scrum Master for Automotive.

1. Introduction to Agile in Automotive Projects

What is Agile?

Agile is an iterative and incremental development approach that focuses on:

- Customer collaboration

- Continuous improvement

- Early and frequent delivery of working software

Why Agile in Automotive Software?

Automotive software development involves:

- Embedded systems (ECUs, ADAS, infotainment)

- Frequent requirement changes (regulations, safety, customer features)

- Integration with hardware

Agile helps by:

- Delivering software in small increments

- Detecting integration issues early

- Improving cross-functional collaboration (software, hardware, testing)

2. Scrum Framework Overview

What is Scrum?

Scrum is an Agile framework used to manage complex software projects using time-boxed iterations called Sprints.

Core Elements of Scrum

Scrum consists of:

- Roles

- Events

- Artifacts

3. Scrum Roles (Automotive Context)

1. Scrum Master

Primary Responsibilities:

- Facilitates Scrum events

- Removes impediments

- Coaches team on Agile principles

- Ensures Scrum is followed correctly

Automotive Example:

- Resolving dependency issues between ECU software and hardware teams

- Addressing delays due to CAN communication issues

2. Product Owner

Responsibilities:

- Owns the Product Backlog

- Defines priorities

- Represents customer and regulatory needs (ISO, ASPICE)

Automotive Example:

- Prioritizing ADAS safety features over infotainment updates

3. Development Team

Characteristics:

- Cross-functional (developers, testers, integration engineers)

- Self-organizing

- Typically 5–9 members

Automotive Example:

- Embedded C developers

- AUTOSAR engineers

- Validation and HIL testers

4. Scrum Artifacts

Product Backlog

- Ordered list of features, bug fixes, technical tasks

- Owned by Product Owner

Automotive Example Items:

- Implement adaptive cruise control logic

- Fix CAN message timing issue

- Integrate new sensor driver

Sprint Backlog

- Subset of Product Backlog selected for a Sprint

- Includes tasks and acceptance criteria

Increment

- Working, tested software at the end of each Sprint

- Must meet Definition of Done

Automotive Definition of Done Example:

- Code reviewed

- Unit tested

- MISRA compliant

- Integrated with ECU build

5. Scrum Events (Ceremonies)

4

Sprint

- Fixed duration (usually 2–3 weeks)

- Goal: deliver a usable software increment

Sprint Planning

Purpose:

- Define Sprint Goal

- Select backlog items

- Break work into tasks

Automotive Focus:

- Hardware availability

- Integration dependencies

- Safety constraints

Daily Scrum (Stand-up)

3 Key Questions:

- What did I do yesterday?

- What will I do today?

- Any blockers?

Scrum Master Role:

- Identify blockers (tool issues, hardware delays)

- Follow up after the meeting

Sprint Review

- Demonstrate working software

- Gather feedback from stakeholders

Automotive Example:

- Demo lane-keeping assist feature on simulation or test bench

Sprint Retrospective

- Inspect and improve team processes

- Identify what went well and what needs improvement

6. Sprint Planning & Execution in Automotive Projects

Sprint Planning Steps

- Review Product Backlog

- Define Sprint Goal

- Estimate effort (story points)

- Identify dependencies (hardware, suppliers)

- Commit to Sprint Backlog

Execution Best Practices

- Continuous integration with ECU builds

- Early testing using simulators or HIL

- Frequent communication with hardware teams

7. Monitoring Progress & Addressing Challenges

Common Automotive Agile Challenges

- Hardware dependency delays

- Supplier integration issues

- Safety and compliance constraints

- Long testing cycles

Scrum Master Techniques

- Use impediment board

- Conduct dependency mapping

- Facilitate cross-team synchronization

- Encourage automation (CI/CD, testing)

Agile Metrics

- Sprint Burndown Chart

- Velocity

- Defect leakage

- Sprint predictability

8. Scrum Management Tools – Jira

Jira is widely used for Scrum project management.

Key Jira Features for Scrum Masters

- Product & Sprint Backlogs

- Scrum boards

- Burndown charts

- Velocity reports

- Issue tracking

Jira Workflow for Automotive Projects

- Create Epics (ADAS, Infotainment, Body Control)

- Break into User Stories

- Assign Story Points

- Plan Sprint

- Track progress daily

- Review reports after Sprint

Jira Issue Types (Example)

- Epic: Autonomous Parking

- Story: Implement ultrasonic sensor logic

- Task: Write sensor interface code

- Bug: Fix CAN timeout issue

9. Role of Scrum Master in Automotive Success

Key Skills Required

- Strong Agile & Scrum knowledge

- Embedded systems understanding

- Communication & facilitation skills

- Conflict resolution

- Tool proficiency (Jira, Confluence)

Scrum Master Value Addition

- Faster delivery of automotive features

- Reduced integration risks

- Improved team morale

- Higher product quality

10. Summary Cheat Sheet

- Scrum is ideal for complex automotive software

- Scrum Master is a servant leader

- Focus on people, process, and delivery

- Jira helps visualize and manage work

- Continuous improvement is key